## Sheet1
PBI | [5 empty] | Tasks
PBI # | User Story | Acceptance Criteria | Definition of Done | Effort | PBI Author | Not Started |  | In Progress | Complete
1 | As an Election Official I want fair OPL and IR election. | The election runs fairly when multiple way ties are encountered. This implies that regardless of how the candidates are listed each one has a fair chance of wnning a tie breaker. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Medium | Jonathan Leibovich | Remove ability to decide a tie in all compareTo functions | Test integration of the tie system in the election simulation
[6 empty] | Add determine tie function to Election | Write test CSV file
[6 empty] | Implement tie function in run election functions | Add documentation
Test new tie function
2 | As an Election Official I want to run an election using multiple election files. | Users can enter multiple file into the system, and the application runs the election will still run correctly. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Small | Varun Reddy | In Main class, prompt user to bring in multiple files | Write test CSV files
[6 empty] | Change constructor of Election to handle multiple files | Add documentation
Preprocess all the given files
Write tests for multiple file handling
3 | As an Election Official I want ballots to be invalidated in IR elections based off the new guidelines set by state officials. | IRV elections are run fairly according to the new guidlines by invalidating ballots without half of their candidates ranked (rounded up from .5 or above to the next highest integer value). | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Medium | Jonathan Leibovich | Count number of candidates ranked for each ballot
Skip ballots with less than half of the candidates ranked
Add documentation
Update Current IRV Test class to account for the invalidated ballots
4 | As an Election Official I want to be able to use a Popularity Only election file in case state officials decide to run Popularity Only elections in the future. | Correctly loads in the data from PO election files. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Small | Tanner Skluzacek | Create new initialization method for Popularity only elections | Write test class for PO elections
Add a check for popularity only elections
Create PO test csv files
Add documentation