## Sheet1
PBI | [5 empty] | Tasks
PBI # | User Story | Acceptance Criteria | Definition of Done | Effort | PBI Author | Not Started | In Progress | Complete
1 | As an Election Official I want fair OPL and IR election. | The election runs fairly when multiple way ties are encountered. This implies that regardless of how the candidates are listed each one has a fair chance of wnning a tie breaker. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Medium | Jonathan Leibovich |  |  | Write test CSV file - Tanner | Test new tie function ?- Varun
[7 empty] | Add documentation - Varun | Remove ability to decide a tie in all compareTo functions - Varun | Updated old tests for modifed functions -Varun
[8 empty] | Add determine tie function to Election - Varun | Test integration of the tie system in the election simulation- Varun
Implement tie function in run election functions - Varun
2 | As an Election Official I want to run an election using multiple election files. | Users can enter multiple file into the system, and the application runs the election will still run correctly. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Small | Varun Reddy |  |  | In Main class, prompt user to bring in multiple files - Toby | Write tests for multiple file handling - Tanner
[7 empty] | Add documentation - Toby | Change constructor of Election to handle multiple files - Toby | Preprocess all the given files - Toby
[7 empty] | Add new tests to test logs - Tanner | Write test CSV files - Tanner | Add multi-file handling for PO init - Toby
Change tests to pass in an ArrayList of files - Tanner
3 | As an Election Official I want ballots to be invalidated in IR elections based off the new guidelines set by state officials. | IRV elections are run fairly according to the new guidlines by invalidating ballots without half of their candidates ranked (rounded up from .5 or above to the next highest integer value). | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Medium | Jonathan Leibovich |  |  | Count number of candidates ranked for each ballot - Jon | Add Invalidate method unit test - Jon
Skip ballots with less than half of the candidates ranked - Jon
Add documentation - Jon
Update Current IRV Test class to account for the invalidated ballots - Jon
4 | As an Election Official I want to be able to use a Popularity Only election file in case state officials decide to run Popularity Only elections in the future. | Correctly loads in the data from PO election files. | VCS (Voting Count System) passes all current unit, system, and regression tests. The code has been refactored. Documentation has been updated. | Small | Tanner Skluzacek |  | Add new tests to test logs - Jon | Create new initialization method for Popularity only elections - Jon | Add documentation - Jon
[8 empty] | Add a check for popularity only elections - Jon | Create PO test csv files - Tanner
[8 empty] | Create a PO Ballot class - Jon | Write test class for PO elections - Tanner
Create PO Ballot Tests - Jon